## Gantt Chart
	Proposal Report				#DIV/0!
	Felerest
	Fatih Eser		Friday, October 25, 2019

										44					45					46					47					48					49					50					51					52					01					02					03					04					05					06					07					08					09					10					11					12					13					14					15					16					17
WBS	Task Names	Resource Names	Start	Duration	Finish	% Complete	Calendar days	Days Completed	Days Remaining	Oct-19					Nov-19					Dec-19					Jan-20					Feb-20					Mar-20					Apr-20
	Proposal Report		25/10/19	4	30-Oct-2019 00:00	#DIV/0!	6			25/10/19	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22
	Introduction	Internet	25/10/19	4	30-Oct-2019 00:00	50%	6	7	13
	Motivation		25/10/19	1	26-Oct-2019 00:00		2	0	1
	Problem Statement		26/10/19	1	27-Oct-2019 00:00	100%	2	1	0
	Scope		27/10/19	1	28-Oct-2019 00:00	50%	2	0	1
	Social Impact		28/10/19	1	29-Oct-2019 00:00	33%	2	0	1
	Related Work		29/10/19	1	30-Oct-2019 00:00		2	0	1

	Team Organization	Internet	25/10/19	1	26-Oct-2019 00:00	83%	2	6	9
	Graph Drawing		25/10/19	1	26-Oct-2019 00:00	100%	2	1	0
	Explanation		25/10/19	1	26-Oct-2019 00:00	100%	2	1	0
	Introducıng Each Person		25/10/19	1	26-Oct-2019 00:00	50%	2	0	1

	Requirement Analysis	Internet	25/10/19	1	26-Oct-2019 00:00	50%	2	3	7
	Requirements		25/10/19	1	26-Oct-2019 00:00		2	0	1
	Objectives		25/10/19	1	26-Oct-2019 00:00	100%	2	1	0
	Drawing Object Tree		25/10/19	1	26-Oct-2019 00:00	50%	2	0	1

	Solution Procedure	Internet	25/10/19	1	26-Oct-2019 00:00	50%	2	1	4
	General Solution Procedure		25/10/19	1	26-Oct-2019 00:00		2	0	1
	Mechanic Parts		25/10/19	1	26-Oct-2019 00:00	100%	2	1	0
	Electronic Parts		25/10/19	1	26-Oct-2019 00:00	50%	2	0	1
	Computer Vision		25/10/19	1	26-Oct-2019 00:00	33%	2	0	1
	Backend Development		25/10/19	1	26-Oct-2019 00:00		2	0	1

	Deliveribles	Internet	25/10/19	1		#DIV/0!	-43762	0	0

	Conclusion	Internet	25/10/19	1		#DIV/0!	-43762	0	0

	Gantt Chart Template V1.1
	Author: Fernando Ribeiro <pinguim.ribeiro@gmail.com>

	How To Use
	INSERT LINES:
	Insert the required number of lines: click the line number and drag down
	From the template, copy the required section or just one line
	INPUT DATA:
	WBS: to itemize the WBS copy and past the required level from the template
	Enter a Task and Resource Names
	Enter a [Start] date and a [Duration] (working days); The Due date is calculated and the task bar shows the task's duration on calendar.
	Or: Enter a [Start] and [Due] dates; The [Duration] (working days) is calculated and the task bar shows the task's duration on calendar.
	Enter a percentage in the [% Complete box]; the task bar shows a progress bar to indicate what percentage of the task is complete.
	Milestone: If you enter a start date without an end date, a milestone marker is displayed on the bar chart.
	In Categories tasks (level 1) Start, Due, Duration and Percentage Complete values are calculated; however they can be overwritten.